## Slide 1
Slide for Meeting Agenda

## Slide 2
CANUTILLO ISD CBAC MEETING | June 23, 2025
Citizens Bond Advisory
Committee Meeting (CBAC)

## Slide 3: CANUTILLO INDEPENDENT SCHOOL DISTRICT 2024 Bond Program
Note- The 2024 Bond Website will be updated based on the information provided and approved by CISD in this report.
The 2024 Monthly Budget Report and Program Schedule are uploaded to the 2024 CISD Bond Website.
Voters in the Canutillo Independent School District passed the historic Canutillo Bond 2024 on May 4, 2024. Canutillo Bond 2024 is the largest per-capita bond ever approved in El Paso County and is a catalyst program in helping Canutillo modernize existing campuses, address continued growth within the District’s boundaries and upgrade the District’s safety and security infrastructure.

## Slide 4: 2024 CISD Bond Program – CBAC Officers
Christian Lopez – Secretary
Antonio Castillo - Chair

## Slide 5: PROCEDEO TEAM MEMBERS TO DATE
Ernesto Ortiz
Program Director
Pamela Soto
Communications Manager
David Martinez Jr.
Controls Manager
Peter Aguilar
Design Manager, IN2
Raquel Bitar
Program Coordinator
Irene Nigaglioni, FAIA
Senior Design Manager, IN2
Alec Kleinhans
Project Manager
Anthony Mariscal
Construction Manager
Corina Heredia
Procurement Manager
Karla Holguin
Owners Assistant Representative
Gabriel Damian
Controls Assistant

## Slide 6: 2024 Bond Program Status – Program Status Update Since our last Quarterly Update…
Board Meetings
04/27 Commissioning RFQ’s
05/27 Third Party RFQ’s
06/17 Design Development
06/XX Land Purchase – Davenport ES
Coordination
Webex System District Upgrades
Wi-Fi Upgrades
Third Party RFQs
Interactive Flat Panels
Security Camera Installation
Principal FF&E Budget
Design/CMAR
Project Design Meetings
05/06-07 Furniture Fair
Land Survey Coordination
AE/CMAR Project Design Review
AE/CMAR Project Cost Discussions
Community Engagement
04/17 Virtual Community Meeting
04/21 Community Meeting
05/02 CAFÉ Golf Tournament
05/14 Davenport ES Spring Carnival
March 25, 2025
June 23, 2025

## Slide 7: 2024 Bond Program Status – Community Engagement
Damian ES Technology Upgrades
May 2025

## Slide 8: 2024 Bond Program Status – Community Engagement
Damian/Garcia ES Security Camera Upgrades
May 2025

## Slide 9: 2024 Bond Program Status – Community Engagement
Alderete MS Bond Signage Unveiling
April 14, 2025

## Slide 10: 2024 Bond Program Status – Community Engagement
NW Early College Bond Signage Unveiling
April 14, 2025
2024

## Slide 11: 2024 Bond Program Status – Community Engagement
Davenport ES Bond Signage Unveiling
April 14, 2025
2024

## Slide 12: 2024 Bond Program Status – Community Engagement
CAFÉ Golf Tournament
May 02, 2025
PROCEDEO Title
Sponsor

## Slide 13: 2024 Bond Program Status – Community Engagement
2024
District-wide Furniture Fair Expo
May 06-07, 2025

## Slide 14: 4yr 2024-2028
CATEGORY | Budget Managed by PROCEDEO | Total
New Facilities/Renovations for 10 Projects | $ 378,955,000 | $ 378,955,000
Interest Earned to Date | $ 477,502 | $ 477,502
Canutillo ISD 2024 Bond Program Total | $ 379,432,502 | $ 379,432,502
Encumbered to Date |  | $ 27,652,484
Amount Paid to Date |  | $ 23,173,069
Forecasted Additional Commitments |  | $ 328,129,447
Interest Earned to Date |  | $ 477,502
Total |  | $ 379,432,502
15.5% Cost Committed to Date
84.5% Forecasted Additional Commitments
2024 Bond Program Status – Overall Budget
10
PROJECTS
$379M
PROPOSITION A

## Slide 15: 2024 Bond Program Status – Program Schedule June 5, 2025
Design NTP
Project | 2024 |  | 2025 |  | 2026 | 2027
Canutillo HS |  |  |  |  |  | 
Canutillo ES |  |  |  |  |  | 
Childress ES |  |  |  |  |  | 
Damian ES |  |  |  |  |  | 
Garcia ES |  |  |  |  |  | 
Reyes ES |  |  |  |  |  | 
NW Early College HS |  |  |  |  |  | 
Canutillo MS* |  |  |  |  |  | 
Alderete MS* |  |  |  |  |  | 
Davenport ES* |  |  |  |  |  | 
10/22/24 |  | TODAY |  | *Schedule subject to change; verify with Program Director |  | 

## Slide 16: 999-001 District Security Upgrades
Project Updates
Security Upgrades*
 | Update | Wi-Fi | Cameras | Webex – Phase 1 | Webex – Phase 2 | Vestibule
1 | Reyes ES | Complete | In Progress | Complete | Complete | Existing
2 | Damian ES | Complete | Complete | Complete | Complete | New Construction
3 | Garcia ES |  | Complete | Complete |  | New Construction
4 | Childress ES |  |  | Complete |  | New Construction
5 | Canutillo ES |  |  | Complete |  | New Construction
6 | Canutillo HS |  |  | Complete |  | Upgrade Existing
Total Budget | $ 1,412,680
Project Type | Renovation
Contractor | UDT / CMAR
Total Project Size | District Wide
Tentative Completion Date | August 2026
General Scope
Safety & Security Upgrades Include:
1-to-1 Camera Replacements
New Cameras at Campus Blind Spots
Webex District Security System for District Emergency Response Accessible via New Phones, App, & Wi-fi Calling
Secure Entry Vestibule Upgrade
District Security Assessment
General Scope
Technology Upgrades Include:
Interactive Flat Panels at all Classrooms and throughout Campuses – Fixed and/or Movable
CISD Design Guidelines - Typical Secure Vestibule Upgrade
*Security upgrades for Webex and Access Control district-wide
Overall Paid to Date
52%

## Slide 17: 001-001 Canutillo HS 6675 S Desert Blvd, El Paso, TX 79932
Design
75%
Project Budget
Project Floor Plan
Pre-Con NTP
October 23, 2024
Design NTP
October 22, 2024
GMP
Construction NTP
Pending
 | Update | Context/Resolution
1 | Baseball/Softball Playfields Reached Substantial Completion 01/13! | Playfields Ribbon Cutting Ceremony took place 02/07
2 |  | 
3 |  | 
Total Budget | $ 16,375,565
CMAR GMP | $--
Owner Contingency | $--
Construction Overall Paid to Date
4% 6%
Project Type | Renovation
Architect | GA Architecture
Contractor (CMAR) | AO General Contractors
Total Project Size | 80,000 SF
Tentative Construction Start | August 2025
Tentative Substantial Completion | Summer 2026
Possible Alternates Contingent on Project Savings:
Exterior Sidewalk, Reseal All Pavement
Replace/Repair Window Wall Gaskets, Reseal Exterior Masonry
Ceiling Replacement
Instructional Technology
New Basketball & Tennis Courts
General Scope
Safety & Security – Vestibule, PA/Fire Alarm/Security Cameras/Access Control System Upgrades
Roofing Repairs, Metal Roof & Canopies
New Cooling Towers, Boilers, Heat Pumps, Replace Evaporative Cooling System
CTE Upgrades
New Wireless Access Points
New Softball/Baseball Playfields Lighting
Project Checklist | 
NA | Re-Zoning/Re-Platting
✓ | Civil Survey
✓ | Geotechnical Report
✓ | Roofing Assessment
✓ | Sewer Scope & Report
NA | Utility Agreements – EPW/EPE/TGS/Comms
✓ | Site Visit/Assessments with AE/CMAR
✓ | 50% CDs Page Turn Meeting
✓ | Pricing/Value Engineering Negotiations
NA | Purchase Sales Agreement
NA | Traffic Impact Analysis
Project Updates

## Slide 18: 101-001 Canutillo ES 651 Canutillo Ave, Canutillo, TX 79835
Design
95%
Construction
0%
Project Budget
Project Floor Plan
Pre-Con NTP
October 23, 2024
Design NTP
October 22, 2024
GMP
Construction NTP
Pending
 | Update | Context/Resolution
1 | Ongoing Coordination for Upcoming Wi-fi, Security Camera, and Access Control Upgrades | 
2 | Webex Phase 1 complete | 
3 |  | 
Total Budget | $ 9,570,316
CMAR GMP | $--
Owner Contingency | $--
3%
Overall Paid to Date
Project Type | Renovation
Architect | GA Architecture
Contractor (CMAR) | Banes General Contractors
Total Project Size | 80,000 SF
Tentative Construction Start | July 2025
Tentative Substantial Completion | Early 2026
Possible Alternates Contingent on Project Savings:
New Bus Access Route
New Sprinkler System, Water Heater Replacement, Reseal All Pavement, Replace Window Blinds, Replace Mechanical Units
General Scope
Safety & Security Upgrades – Vestibule, Fire Alarm/PA/Emergency Notification Systems, Security Cameras & Access Control
Network Infrastructure & Wireless Access Points
Replace HVAC Units
New Roofing & Repairs to Parapets
Project Checklist | 
NA | Re-Zoning/Re-Platting
✓ | Civil Survey
✓ | Geotechnical Report
✓ | Roofing Assessment
✓ | Sewer Scope & Report
NA | Utility Agreements – EPW/EPE/TGS/Comms
✓ | Site Visit/Assessments with AE/CMAR
✓ | 90% CDs Page Turn Meeting
✓ | Pricing/Value Engineering Negotiations
NA | Purchase Sales Agreement
NA | Traffic Impact Analysis
Project Updates

## Slide 19: 104-001 Childress ES 7700 Cap Carter Rd. Vinton, Texas 79821
Design
Project Budget
Project Floor Plan
Pre-Con NTP
October 23, 2024
Design NTP
October 22, 2024
GMP
Construction NTP
Pending
Total Budget | $ 7,269,598
CMAR GMP | $--
Owner Contingency | $--
100%
Construction Overall Paid to Date
0% 3%
Project Type | Renovation
Architect | Mijares-Mora Architects
Contractor (CMAR) | Jordan Foster Construction
Total Project Size | 80,000 SF
Tentative Construction Start | July 2025
Tentative Substantial Completion | Spring 2026
Possible Alternates Contingent on Project Savings:
Replace Black-Top
Replace Carpet Flooring with LVT
Replace Millwork & Sinks at Classrooms
Shade Structures at Soccer Field
Renovate Science, Computer Labs and Library – flooring, paint millwork, lights
General Scope
Safety & Security Upgrades – Vestibule, Fire Alarm/PA/Emergency Notification Systems, Security Cameras & Access Control
Roof Maintenance – Sealants & Walk Pad
New HVAC Units
Infrastructure Upgrades – Network Switches & Cabling, Wi-Fi
Project Checklist | 
NA | Re-Zoning/Re-Platting
✓ | Civil Survey
✓ | Geotechnical Report
✓ | Roofing Assessment
✓ | Sewer Scope & Report
NA | Utility Agreements – EPW/EPE/TGS/Comms
✓ | Site Visit/Assessments with AE/CMAR
✓ | 90% CDs Page Turn Meeting
✓ | Pricing/Value Engineering Negotiations
NA | Purchase Sales Agreement
NA | Traffic Impact Analysis
Project Updates

## Slide 20: 103-001 Damian ES 6300 Strahan Rd, El Paso, TX 79932
Design
100%
Construction
0%
Project Budget
Project Floor Plan
Pre-Con NTP
October 23, 2024
Design NTP
October 22, 2024
GMP
Construction NTP
Pending
 | Update | Context/Resolution
1 | Webex Phase 1 /Phase 2 complete | 
2 | Infrastructure Upgrades – Network and Security Cameras Installation Complete | 
3 |  | 
Total Budget | $ 7,299,537
CMAR GMP | $--
Owner Contingency | $--
Overall Paid to Date
7%
Project Type | Renovation
Architect | Mijares-Mora Architects
Contractor (CMAR) | Jordan Foster Construction
Total Project Size | 80,000 SF
Tentative Construction Start | July 2025
Tentative Substantial Completion | Spring 2026
Possible Alternates Contingent on Project Savings:
Additional Student Restrooms
Interior Paint, Seal Masonry Joints
Exterior Stucco & Paint
Replace All Water Heaters
Multipurpose Space
General Scope
Safety & Security Upgrades – Vestibule, Fire Alarm/PA/Emergency Notification Systems, Security Cameras & Access Control
Roof Maintenance – Sealants & Walk Pad
New HVAC Units
Infrastructure Upgrades – Network Switches & Cabling, Wi-Fi
Project Checklist | 
NA | Re-Zoning/Re-Platting
✓ | Civil Survey
✓ | Geotechnical Report
✓ | Roofing Assessment
✓ | Sewer Scope & Report
NA | Utility Agreements – EPW/EPE/TGS/Comms
✓ | Site Visit/Assessments with AE/CMAR
✓ | 90% CDs Page Turn Meeting
✓ | Pricing/Value Engineering Negotiations
NA | Purchase Sales Agreement
NA | Traffic Impact Analysis
Project Updates

## Slide 21: 105-001 Garcia ES 6550 Westside Dr, El Paso, TX 79932
Design
100%
Project Budget
Project Floor Plan
Pre-Con NTP
October 23, 2024
Design NTP
October 22, 2024
GMP
Construction NTP
Pending
 | Update | Context/Resolution
1 | Ongoing coordination for upcoming Wi-Fi, and access control upgrades | 
2 | Webex Phase 1 complete | 
3 | Security Cameras Installation Complete | 
Total Budget | $ 7,007,109
CMAR GMP | $--
Owner Contingency | $--
Construction Overall Paid to Date
0% 3%
Project Type | Renovation
Architect | Mijares-Mora Architects
Contractor (CMAR) | Jordan Foster Construction
Total Project Size | 80,000 SF
Tentative Construction Start | July 2025
Tentative Substantial Completion | Spring 2026
Possible Alternates Contingent on Project Savings:
Clean Existing Ductwork
Replace All Water Heaters
Additional Staff Restrooms
New Interior Paint
New Speaker System & Stage at Gym
Replace Playground Canopies
General Scope
Safety & Security Upgrades – Vestibule, Fire Alarm/PA/Emergency Notification Systems, Security Cameras & Access Control
Roof Maintenance – Sealants & Walk Pad
New HVAC Units
Infrastructure Upgrades – Network Switches & Cabling, Wi-Fi
Project Checklist | 
NA | Re-Zoning/Re-Platting
✓ | Civil Survey
✓ | Geotechnical Report
✓ | Roofing Assessment
✓ | Sewer Scope & Report
NA | Utility Agreements – EPW/EPE/TGS/Comms
✓ | Site Visit/Assessments with AE/CMAR
✓ | 90% CDs Page Turn Meeting
✓ | Pricing/Value Engineering Negotiations
NA | Purchase Sales Agreement
NA | Traffic Impact Analysis
Project Updates

## Slide 22: 106-001 Reyes ES 7440 Northern Pass Dr, El Paso, TX 79911
Design
100%
Construction
0%
Project Budget
Project Floor Plan
Pre-Con NTP
October 23, 2024
Design NTP
October 22, 2024
GMP
Construction NTP
Pending
 | Update | Context/Resolution
1 | Wireless infrastructure upgrades completed November 2024 | 
2 | Webex Phase 1 complete | 
3 |  | 
Total Budget | $ 1,998,731
CMAR GMP | $--
Owner Contingency | $--
24%
Overall Paid to Date
Project Type | Renovation
Architect | GA Architecture
Contractor (CMAR) | Banes General Contractors
Total Project Size | 80,000 SF
Tentative Construction Start | July 2025
Tentative Substantial Completion | Early 2026
Possible Alternates Contingent on Project Savings:
Reseal/Recoat Asphalt Pavements
Artificial Turf Areas & Walking Surface
Metal Shade Structure
General Scope
Safety & Security Upgrades
MEP Backup Chiller & Cooling Tower
Upgrade Network Switches & Cabling, Security Cameras
New Instructional Technology
Wireless Upgrades
Project Checklist | 
NA | Re-Zoning/Re-Platting
✓ | Civil Survey
✓ | Geotechnical Report
✓ | Roofing Assessment
✓ | Sewer Scope & Report
NA | Utility Agreements – EPW/EPE/TGS/Comms
✓ | Site Visit/Assessments with AE/CMAR
✓ | 90% CDs Page Turn Meeting
✓ | Pricing/Value Engineering Negotiations
NA | Purchase Sales Agreement
NA | Traffic Impact Analysis
Project Updates

## Slide 23: 003-001 NW Early College HS 6701 S Desert Blvd, El Paso, TX 79932
Design
50%
Construction
0%
Project Budget
Project Floor Plan
Pre-Con NTP
October 23, 2024
Design NTP
October 22, 2024
GMP
Construction NTP
Pending
 | Update | Context/Resolution
1 | Land Acquisition Update – Pending Ground Lease Agreement | Pending EPCC Board Approval
2 | Ongoing design revisions to reach established project budget | 
3 |  | 
Total Budget | $ 40,458,824
CMAR GMP | $--
Owner Contingency | $--
2%
Overall Paid to Date
Project Type | Renovation
Architect | MNK Architects
Contractor (CMAR) | Jordan Foster Construction
Total Project Size | 45,000 SF
Tentative Construction Start | September 2025
Tentative Substantial Completion | Spring 2027
General Scope
The proposed design includes the construction of 31,140 SF of Academic / Classrooms building, 4,732 SF of Fine Arts
/ Multipurpose building, 8,583 SF of Administration building, 3,704 SF of Athletics building, and 14,748 SF Science Building
Project Checklist | 
NA | Re-Zoning/Re-Platting
✓ | Civil Survey
✓ | Geotechnical Report
NA | Roofing Assessment
NA | Sewer Scope & Report
 | Utility Agreements – EPW/EPE/TGS/Comms
✓ | Site Visit/Assessments with AE/CMAR
 | 90% CDs Page Turn Meeting
✓ | Pricing/Value Engineering Negotiations
 | Ground Lease Agreement
NA | Traffic Impact Analysis
Project Updates

## Slide 24: 041-001 Canutillo MS 6201 Strahan Rd, El Paso, TX 79932
Design
50%
Project Budget
Project Floor Plan
Pre-Con NTP
October 23, 2024
Design NTP
October 22, 2024
GMP
Construction NTP
Pending
 | Update | Context/Resolution
1 | Land Acquisition Update – Closed | 
2 | Ongoing coordination for existing site abatement and demolition scope | 
3 | Design Development Phase – Complete June BOT | 
Total Budget | $ 106,847,954
CMAR GMP | $--
Owner Contingency | $--
Construction Overall Paid to Date
0% 8%
Project Type | New Construction
Architect | DLR Group
Contractor (CMAR) | Banes General Contractors
Total Project Size | 165,000 SF
Tentative Construction Start | November 2025
Tentative Substantial Completion | Late 2027/Early 2028
General Scope
New state-of-the-art 21st Century Learning Facility: Cafeteria, Library, Gymnasium, Admin, Collaboration Spaces, Special Education, New Playfields, New Parking, Bus Loop
Project Checklist | 
✓ | Re-Zoning/Re-Platting
✓ | Civil Survey
✓ | Geotechnical Report
✓ | Roofing Assessment
NA | Sewer Scope & Report
 | Utility Agreements – EPW/EPE/TGS/Comms
✓ | Site Visit/Assessments with AE/CMAR
 | 90% CDs Page Turn Meeting
✓ | Pricing/Value Engineering Negotiations
✓ | Purchase Sales Agreement
✓ | Traffic Impact Analysis
Project Updates

## Slide 25: 042-001 Alderete MS 1634 Resler Dr. El Paso, Texas, 79911
Design
50%
Project Budget
Project Floor Plan
Pre-Con NTP
October 23, 2024
Design NTP
October 22, 2024
GMP
Construction NTP
Pending
 | Update | Context/Resolution
1 | Land Acquisition Update – Closed | 
2 | Design Development Phase – Complete June BOT | 
3 |  | 
Total Budget | $ 106,813,514
CMAR GMP | $--
Owner Contingency | $--
Construction Overall Paid to Date
0% 9%
Project Type | New Construction
Architect | DLR Group
Contractor (CMAR) | Banes General Contractors
Total Project Size | 165,000 SF
Tentative Construction Start | November 2025
Tentative Substantial Completion | Late 2027/Early 2028
General Scope
New state-of-the-art 21st Century Learning Facility: Cafeteria, Library, Gymnasium, Admin, Collaboration Spaces, Special Education, New Playfields, New Parking, Bus Loop
Project Checklist | 
✓ | Re-Zoning/Re-Platting
✓ | Civil Survey
✓ | Geotechnical Report
✓ | Roofing Assessment
NA | Sewer Scope & Report
 | Utility Agreements – EPW/EPE/TGS/Comms
✓ | Site Visit/Assessments with AE/CMAR
 | 90% CDs Page Turn Meeting
✓ | Pricing/Value Engineering Negotiations
✓ | Purchase Sales Agreement
✓ | Traffic Impact Analysis
Project Updates

## Slide 26: 102-001 Davenport ES Enchanted Hills, Unit Seven
Design
50%
Project Budget
Project Floor Plan
Pre-Con NTP
October 23, 2024
Design NTP
October 22, 2024
GMP
Construction NTP
Pending
 | Update | Context/Resolution
1 | Land Acquisition Update – to close by June | 
2 | Design Development Phase – Complete June BOT | 
3 |  | 
Total Budget | $ 73,901,172
CMAR GMP | $--
Owner Contingency | $--
Construction Overall Paid to Date
0% 1%
Project Type | New Construction
Architect | Pfluger Architects
Contractor (CMAR) | LDCM Solutions
Total Project Size | 119,000 SF
Tentative Construction Start | September 2025
Tentative Substantial Completion | Spring 2027
General Scope
New state-of-the-art 21st Century Learning Facility to include 36 TEA (Texas Education Agency) Flexibility Level 3-4 classrooms, collaborative learning spaces, and grade-level neighborhoods, all with a strong emphasis on outdoor connections.
Project Checklist | 
✓ | Re-Zoning/Re-Platting
✓ | Civil Survey
✓ | Geotechnical Report
✓ | Roofing Assessment
✓ | Sewer Scope & Report
 | Utility Agreements – EPW/EPE/TGS/Comms
✓ | Site Visit/Assessments with AE/CMAR
 | 90% CDs Page Turn Meeting
✓ | Pricing/Value Engineering Negotiations
 | Purchase Sales Agreement
✓ | Traffic Impact Assessment
Project Updates

## Slide 27: 2024 Bond Program Status – Quarterly Meeting Schedule
Next Quarterly Meeting Date